Stoke Ferry Neighbourhood Plan Working Group

Monthly report to Stoke Ferry Parish Council

Date: 04.03.2020

1. Work over the past month

- Despite many members of the group coming down with various winter ailments we achieved a great deal.

- Our Project Plan and Timeline have been updated and agreed by the Group.

- The first NP Consultation Day was held on Saturday 15th Feb at the Village Hall.

  - The day focussed on establishing themes and ideas for our DRAFT objectives, and to test to the DRAFT aims and vision of the Plan

  - We collected information about what people love about SF, and what would make SF an amazing place

  - 38 people came and aired their views on the future of our village

  - We also set up an on-line consultation document to enable others to participate in the process

  - Our thanks to all who participated

- An excellent, in-depth, 68-page Data Profile of our Parish has been created by consultant, Emma Harrison. Available on our website (www.stokeferryplan.co.uk) it contains data on:

  - Community & Services

  - Housing and the Built Environment

  - Natural  Environment

  - Business and Employment

- The Working Group met on 24th February to reflect on the Consultation Day and plan for the Second Stage of Consultation: Stakeholder Consultation. We also planned for the forthcoming Village Character Assessment which will inform NP policy and be a reference point for any subsequent design statements.

- Funding: The second funding application to Locality will now not take place until early April

2. Work ahead, over the next month

- Next ‘open to the public’ NPWG Monthly Progress Meeting 1st April at 6pm, SF Village Hall

- Prepare and write up a Village Character Assessment

- Prepare costings for the second funding application

3.  Expenditure update

- Invoice from consultant, Emma Harrison (Data Profile) 16 hours @ £40/hour = £640.00

- Invoice for hire of the Village Hall for First Consultation Day = £70.00

- Invoice from Andy Hayward for cost of Banner for Consultation Days ,Easierprint, Cost £15.63 plus £3.13 VAT. Total £18.76.

- Refreshments for First Consultation Day. Total £66.18

Total: £794.94 – £3.13 Vat = £791.81to be paid from the NP Locality Grant